**ACCESS for ELLs®/Alternate ACCESS for ELLs™**

**2013-2014 Testing Schedule**

|  |  |  |
| --- | --- | --- |
| **Task** | **Start Date** | **End Date** |
| Divisions Order Test Materials (4 weeks) | 10/14/13 | 11/08/13 |
| Divisions Order Pre-ID Labels (4 weeks) | 10/14/13 | 11/08/13 |
| MT**\*** Ships Test Materials to Divisions | 12/16/13 | 12/20/13 |
| Divisions Receive Test Materials |  | 12/20/13 |
| Testing Window (10 weeks) | 1/6/14 | 3/14/14 |
| Additional Materials Deadline |  | 2/28/14 |
| Divisions Pack Completed Materials (1 week) | 3/17/14 | 3/21/14 |
| Divisions Ship Completed Materials to MT |  | 3/21/14 |
| MT Receives All Materials | 3/24/14 | 3/28/14 |
| MT scores and generates reports (8 weeks) | 3/31/14 | 5/23/14 |
| Data Validation Window (2 weeks)**\*\*** | 4/21/14 | 5/2/14 |
| MT Ships Reports to Divisions | 5/26/14 | 5/30/14 |
| Divisions Receive Reports |  | 5/30/14 |

\*MT = MetriTech, Inc.

\*\*The data validation window allows divisions to submit updated student data files to MetriTech. No printed score report correction will be available. School divisions may contact MetriTech with questions by e-mail at [wida@metritech.com](mailto:wida@metritech.com) or by telephone at (800) 747-4868.