## Slide 1: A Timeline for the Revision of Virginia’s Accreditation and Accountability Systems
2022-2023

## Slide 2: Priorities
Bifurcate and redesign the accreditation and accountability systems;
  Accreditation: A measure of school compliance
  Accountability: A measure of school performance based on student outcomes.
Align the federal and state accountability systems to the greatest extent possible; and
Create a clear, concise, timely, and transparent accountability and reporting system so that schools can evaluate year-over-year performance to make improvements, and the community can gauge school effectiveness and quality of programs.
  This revised system will promote communication with parents and families about the performance of the schools serving their students and communities.

## Slide 3: Timeline (1 of 8)
November and December 2022
VDOE staff submits legislative proposals for review to the Governor’s office for statutory changes to bifurcate the accreditation and accountability systems (completed).
VDOE staff hosts a work session with the Board on the work plan/timeline for bifurcating the accreditation and accountability systems (November 16, 2022).
The Board discusses the necessity of emergency regulations for new accountability system regulations (November 16, 2022).

## Slide 4: Timeline (2 of 8)
November and December 2022 (continued)
The Governor’s office submits legislative proposals to the Division of Legislative Services (DLS) to draft omnibus legislation to bifurcate the accreditation and accountability systems.
  VDOE to work with DLS to ensure all references to accreditation in Code are correctly updated.
VDOE staff begins drafting emergency Board regulations that create a new accountability system (November and December 2022).
  Work with consultants on draft language.
  Requirements for emergency regulations, including process and timeline, are outlined in § 2.2-4011.

## Slide 5: Timeline (3 of 8)
January and February 2023
The Governor’s Office and State Superintendent work with the General Assembly to pass omnibus legislation to bifurcate accreditation and accountability systems.
VDOE staff hosts a virtual work session with the Board on reimagining accreditation as compliance and on the components of the new accountability model (January 2023).
VDOE staff brings emergency regulations on the new accountability system to the Board for first review (February 2023).
Impacted VDOE Departments begin scope of work related to this initiative (January 2023).

## Slide 6: Timeline (4 of 8)
March and April 2023
VDOE staff brings emergency regulations on the new accountability system to the Board for final review, concurrently filing the Notice of Intended Regulatory Action to begin the full regulatory process (March 2023).
Impacted VDOE departments continue to align guidance, policies, and practices to new accountability system (March and April 2023).
  Data services begins work on programming the new accountability system (April 2023).

## Slide 7: Timeline (5 of 8)
May and June 2023
Impacted VDOE Departments continue associated work (May and June 2023).
VDOE staff brings the ESSA Consolidated State Plan to the Board for first review (June 2023).
If Code changes are approved by the General Assembly, VDOE staff will start the regulatory process on revising Part VIII of the Standards of Accreditation to remove references to accountability and focus on compliance (June 2023).

## Slide 8: Timeline (6 of 8)
July, August, September, and October 2023
Impacted VDOE Departments continue associated work (July through October 2023).
VDOE staff brings the ESSA Consolidated State Plan to the Board for final review (July 2023).
VDOE will report current accreditation and federal accountability results to schools.
Schools are identified for federal support and improvement in accountability year 2023-2024 based on the current ESSA Consolidated State Plan.
VDOE will announce and report state accountability results based on the emergency regulations.

## Slide 9: Timeline (7 of 8)
July, August, September, and October 2023 (continued)
VDOE staff bring proposed stage regulations to the Board for first review for the new accountability system regulations (September 2023).
VDOE staff bring proposed stage regulations to the Board for final review for the new accountability system regulations (October 2023).

## Slide 10: Timeline (8 of 8)
Beyond October 2023
Receive approval on ESSA Consolidated State Plan that will be used for accountability year 2024-2025.
The Board approves the final stage of the new accountability system regulations in early 2024.
The new accreditation and accountability systems will be used in accountability year 2024-2025 and current systems will no longer be used.
Impacted VDOE Departments continue associated work.

## Slide 11: Impacted Departments
There will be significant implications for departments within VDOE to address the changes that occur as a result of this work.
Office of Accountability
Office of School Quality
Office of Board Relations
Office of Communication (includes updates to the School Quality Profiles)
Office of Policy
Office of Data Services
Office of Technology and Systems Development
Office of Budgeting
Office of STEM and Innovation
Office of Humanities
Office of Program Improvement
Office of Licensure and School Leadership
Office of Facilities and Family Engagement
Office of ESEA Programs