## Slide 1: Virginia Lab Schools and Innovation Network Update
College Partnership Lab School Standing Committee
June 10, 2024

## Slide 2: Overview of Innovative Network
The department is launching upcoming implementation support of approved and pending lab schools to include:
Day One Kit and Overview: Overview and walk through of school opening action step kit for Fall 2024 operational lab schools to ensure “Day One Ready” for all lab schools
Themed Networks: Tiered thematic networks and resource supports for all lab schools including those opening Fall 2024 and those opening Fall 2025
Monthly Calls: Regular call to provide ongoing support, problem solving and networking for operational lab schools beyond start of operations as well as preparation calls for Fall 2025 schools as they plan to open

## Slide 3: Current 2024 Operational Lab Schools
Approved lab schools slated to begin operations in 2024 include:
VCUxCodeRVA (currently operational)
Germanna FEA
UMW ATI
JMU
UVA Innovation Hub
Explore @RC
SWVA-HEALS
GMU DSCA
To ensure a quality start to operations, VDOE, with the support of the associated higher education and K-12 lab school partners and outside resources as necessary, provide resources, establish networks, and continue engagement with Lab Schools during the critical months leading up to and following Day One and beyond.

## Slide 4: Convenings for 2024 Lab Schools
Late July/Early August 2024: Kickoffs with 2024 lab schools and staffs
June 2024
2024 Lab School Summit
Focus on 2024 Opening Schools
Overview and Tactical Next Steps
Late June/July 2024
Individual Consults
Progress check ins
July 2024
Virtual or In person
Compliance Summit
HR, FERPA, Finance, Reporting
August/September 2024
Lab School Kick Offs
DOE staff to support Day One Events

## Slide 5: Phases of Network Focus
Phase I Focal Areas: (April to June 2024)
Hiring
Licensure
Facilities and Safety
Governing Board Selection & Training
Curriculum
Scheduling
Phase II Focal Areas: (June to August 2024)
Finance
Compliance (FERPA, SPED, HR, etc.)
Transportation & Food Service
Community, Student, & Parent Outreach
DOE Reporting
Phase III Focal Areas (August to October 2024)
Media Engagement
Start of School Requirements
Attendance
Performance Evaluations
Operational Fidelity

## Slide 6: Next Steps For Implementation: Update
7/1/24: Finalize Day One Kit
6/15/24: Establish weekly launch check-ins for all Fall 2024 lab schools
By 7/15/24: SY24 Lab School Summit
August 24: On-site visits to all SY24 Lab Schools
Continue to support sustainability through activation of business and industry partner networks
Support 2025 lab schools during start-up year (facilities, hiring, curriculum, scheduling, recruitment and enrollment, etc.)
Continue to develop and mobilize as-needed resources for all lab schools